# Sample Special Events Timeline

Concert or Performance

Week 30 (or earlier):

- Select and confirm artists. Use personal contacts if possible. Send a letter describing the event and its purpose, the organization’s work and its goals, and others who are involved or who have been involved in the past.

- Confirm details with artist’s manager and/or publicist.

- Review contract(s) with appropriate (pro bono if you’re lucky) attorney.

- Identify and confirm volunteer co-chairs.

- Select a date. The artist’s availability will be the major factor. Other considerations include the venue’s availability, competing events, day of the week, and appropriateness of the season.

- Select and confirm the venue. Factors to consider are choosing a location suited to the artist’s following, union or non-union venue (affects costs), available parking and public transportation, public safety, and accessibility to people with disabilities.

- Hire technical crew and security.

- Arrange insurance.

- Make travel arrangements for artist(s).

- Hire/recruit publicity and promotions staff.

- Apply for any needed city permits (for such things as closing off a street corner, redirecting traffic, renting portable toilets and portable booths, food concessions, liquor sales, and unusual visual and sound effects — such as fireworks).

Weeks 13–15

- Publicity and promotion begin: Organize/develop media list, check on listing deadlines, select poster design.

- Choose method of ticket sales: Contract with ticket service or handle within your organization; contract with web sales service (unless your organization already sells things online).

- Co-chairs help with lists of contacts: invitees, donors of services, media, and volunteers.

- Hire technical staff, including stage and house managers, sound and light designers, disc jockeys, masters of ceremonies, and so on.

- Obtain hall/theater specifications from venue and stage/technical needs from artist.

- Work with technical crew to select needed equipment. If not available within venue, contract sound and lighting (and fireworks) companies.

- Recruit and organize volunteers by skills and availability.

- Design and prepare promotional materials such as buttons and T-shirts.

- Recruit and brief a knowledgeable speaker (maybe your board chair) to speak at the event.

# Weeks 10–12

- Print and distribute posters and fliers.

- Begin ticket sales.

- Distribute news releases.

- Write and distribute public service announcements to radio and TV stations.

- Plan a news conference (if you have a compelling idea that would attract attention) or smaller-scale promotion like ticket giveaways on the radio.

- Estimate needed security staff and hire security.

- Compare artist’s stage plots to hall specifications and double-check about any additional needed equipment.

- Plan event volunteer needs.

Weeks 5–9

- Assess volunteers’ skills and assign them to committees/tasks.

- Plan and secure needed materials for information tables, booths, and concessions.

- Make follow-up calls to the media.

- Schedule production crew meeting.

Weeks 3–4

- Produce news conference or other media promotion.

- Develop time schedule for the event.

- Meet with technical crews, house managers, master of ceremonies, and other key staff to review and refine time schedule.

- If you expect a large crowd, contract with and confirm medical staff.

- Arrange food for event staff day-of-show.

- Arrange food and beverages for artist’s dressing rooms.

- Arrange comp tickets and artist’s passes for guests and media.

Weeks 1–2

- Make follow-up calls to previously mailed news releases.

- Coordinate radio and TV interviews.

- Prepare media packets.

- Hold final walk-through with technical staff and security chief.

- Make sure guest artist(s) have provided specific instructions for setting up sound and lighting systems and confirm the venue’s and crew’s capacity to follow them.

- Prepare for sales of T-shirts, buttons, and other merchandise.

- Organize backstage passes.

- Confirm all volunteers and their roles.

- Confirm artist’s travel and accommodations.

Day before show

Compile event necessities, including:

- Cash boxes with change in appropriate denominations

- Receipts

- Credit card equipment and receipts

- Literature about your organization

- Merchandise to sell

- Sign-up lists and guest lists

- Backstage pass lists

- Ice chests and bottled water

- Name tags for committee members and volunteers

- Emergency numbers for police, fire, security, and medical staff

- All contact phone numbers (artist’s hotel, hosts, speakers, suppliers)

- Emergency cash

- Poster board

- Signs

- First-aid kit

- Microphones and sound system (if facility doesn’t have them)

Day of show

- Pick up artist at the airport or hotel.

- Send artist flowers/candy/other complimentary items.

- Greet media and distribute media packets.

- Coordinate complimentary tickets and guest passes.

- Distribute backstage passes.

- Check on technical set up of sound and lighting equipment.

- Check with stage manager and house manager to keep event on schedule.

- Check with event security staff.

- Set up and monitor sales of concessions.

- Arrange meals for staff and artists.

- Clean up.

- Count your proceeds!

Post-show

- Thank and recognize artist, volunteers, and crew.

- Hold a follow-up meeting with organizers to discuss what worked and what didn’t work.

- Prepare notes for your files and/or the next event coordinators.